## Bugs Overview
Bug Id | Summary | Environment | Browsers Platforms & Version | Priority | Severity | Steps to reproduce | Expected result | Actual result | Attachments | Reported by | Reported on | Status
Bug01 | Incorrect filtering of books by review on categories page | Windows 10 | Opera GX 109 | High | Major | 1.Navigate to the categories page 2.Click on the filter option for Five-Star reviews | Only books with a five-star review should be shown on the page | Books with four-star reviews are also displayed on the page |  | Stefan Tasevski | 01.06.2024 | Open
Bug02 | Book fails to add to product comparison and results in infinite loading | Windows 10 | Opera GX 109 | High | Major | 1. Navigate to the categories page 2. Hover over a book cover 3.Click on the compare button (two arrows pointing left and right) | The book should be added to the product comparison list | The page enters an infinite loading state and the book is not added to the product comparison |  | Stefan Tasevski | 01.06.2024 | Open
Bug03 | User can rename wishlist with a title that is too short | Windows 10 | Opera GX 109 | Medium | Moderate | 1. Navigate to the wishlist page 2. Click on the wishlist name field 3.Enter a new wishlist name that is too short ( Book ) 4. Click on the checkmark next to the wishlist name field | The new name should not be saved successfully and an error message should be displayed | The user is able to rename the wishlist name and the change is saved successfully without any error message |  | Stefan Tasevski | 01.06.2024 | Open
Bug04 | User can rename wishlist with a title that is too long | Windows 10 | Opera GX 109 | Medium | Moderate | 1. Navigate to the wishlist page 2. Click on the wishlist name field 3. Enter a new wishlist name that is too long ( This title is way too long to be accepted and should be rejected ) 4. Click on the checkmark next to the wishlist name field | The new name should not be saved successfully and an error message should be displayed | The user is able to rename the wishlist name and the change is saved successfully without any error message |  | Stefan Tasevski | 01.06.2024 | Open
Bug05 | User can rename wishlist with titles that include invalid special characters | Windows 10 | Opera GX 109 | Medium | Moderate | 1. Navigate to the wishlist page. 2. Click on the wishlist name field 3. Enter a new wishlist name that includes invalid special characters (MyBooks!) 4. Click on the checkmark next to the wishlist name field | The new name should not be saved successfully and an error message should be displayed | The user is able to rename the wishlist name and the change is saved successfully without any error message |  | Stefan Tasevski | 01.06.2024 | Open
Bug06 | Order is successfully placed with more than maximum characters in the first name field | Windows 10 | Opera GX 109 | High | Major | 1. Navigate to the checkout page with one or more books in the cart 2. Enter "ThisNameIsWayTooLongForTheField" in the First Name field 3. Enter "Tasevski" in the Last Name field 4. Enter "Hollywood Boulevard" in the Street Address field 5. Enter "Los Angeles" in the Town/City field 6. Enter "90001" in the Zip Code field 7. Enter "+19512390523" in the Phone field 8. Enter "brainster1@gmail.com" in the Email Address field 9. Click on the Place Order button | An error message should be displayed and the order should not be placed successfully | The order is successfully placed without any error message |  | Stefan Tasevski | 01.06.2024 | Open
Bug07 | Order is successfully placed with less than minimum characters in the first name field | Windows 10 | Opera GX 109 | High | Major | 1. Navigate to the checkout page with one or more books in the cart 2. Enter "S" in the First Name field 3. Enter "Tasevski" in the Last Name field 4. Enter "Hollywood Boulevard" in the Street Address field 5. Enter "Los Angeles" in the Town/City field 6. Enter "90001" in the Zip Code field 7. Enter "+19512390523" in the Phone field 8. Enter "brainster1@gmail.com" in the Email Address field 9. Click on the Place Order button | An error message should be displayed and the order should not be placed successfully | The order is successfully placed without any error message |  | Stefan Tasevski | 01.06.2024 | Open
Bug08 | Order is successfully placed with characters that are not Latin or Cyrillic in the first name field | Windows 10 | Opera GX 109 | High | Major | 1. Navigate to the checkout page with one or more books in the cart 2. Enter "스테판" in the First Name field 3. Enter "Tasevski" in the Last Name field 4. Enter "Hollywood Boulevard" in the Street Address field 5. Enter "Los Angeles" in the Town/City field 6. Enter "90001" in the Zip Code field 7. Enter "+19512390523" in the Phone field 8. Enter "brainster1@gmail.com" in the Email Address field 9. Click on the Place Order button | An error message should be displayed and the order should not be placed successfully | The order is successfully placed without any error message |  | Stefan Tasevski | 01.06.2024 | Open
Bug09 | Order is successfully placed with invalid special characters in the first name field | Windows 10 | Opera GX 109 | High | Major | 1. Navigate to the checkout page with one or more books in the cart 2. Enter "Stefan@" in the First Name field 3. Enter "Tasevski" in the Last Name field 4. Enter "Hollywood Boulevard" in the Street Address field 5. Enter "Los Angeles" in the Town/City field 6. Enter "90001" in the Zip Code field 7. Enter "+19512390523" in the Phone field 8. Enter "brainster1@gmail.com" in the Email Address field 9. Click on the Place Order button | An error message should be displayed and the order should not be placed successfully | The order is successfully placed without any error message |  | Stefan Tasevski | 01.06.2024 | Open
Bug010 | Order is successfully placed with numbers in the first name field | Windows 10 | Opera GX 109 | High | Major | 1. Navigate to the checkout page with one or more books in the cart 2. Enter "Stefan777" in the First Name field 3. Enter "Tasevski" in the Last Name field 4. Enter "Hollywood Boulevard" in the Street Address field 5. Enter "Los Angeles" in the Town/City field 6. Enter "90001" in the Zip Code field 7. Enter "+19512390523" in the Phone field 8. Enter "brainster1@gmail.com" in the Email Address field 9. Click on the Place Order button | An error message should be displayed and the order should not be placed successfully | The order is successfully placed without any error message |  | Stefan Tasevski | 01.06.2024 | Open
Bug011 | Order is successfully placed with more than maximum characters in the last name field | Windows 10 | Opera GX 109 | High | Major | 1. Navigate to the checkout page with one or more books in the cart 2. Enter "Stefan" in the First Name field 3. Enter "ThisLastNameIsTooLongForTheField" in the Last Name field 4. Enter "Hollywood Boulevard" in the Street Address field 5. Enter "Los Angeles" in the Town/City field 6. Enter "90001" in the Zip Code field 7. Enter "+19512390523" in the Phone field 8. Enter "brainster1@gmail.com" in the Email Address field 9. Click on the Place Order button | An error message should be displayed and the order should not be placed successfully | The order is successfully placed without any error message |  | Stefan Tasevski | 01.06.2024 | Open
Bug012 | Order is successfully placed with less than minimum characters in the last name field | Windows 10 | Opera GX 109 | High | Major | 1. Navigate to the checkout page with one or more books in the cart 2. Enter "Stefan" in the First Name field 3. Enter "T" in the Last Name field 4. Enter "Hollywood Boulevard" in the Street Address field 5. Enter "Los Angeles" in the Town/City field 6. Enter "90001" in the Zip Code field 7. Enter "+19512390523" in the Phone field 8. Enter "brainster1@gmail.com" in the Email Address field 9. Click on the Place Order button | An error message should be displayed and the order should not be placed successfully | The order is successfully placed without any error message |  | Stefan Tasevski | 01.06.2024 | Open
Bug013 | Order is successfully placed with characters that are not Latin or Cyrillic in the last name field | Windows 10 | Opera GX 109 | High | Major | 1. Navigate to the checkout page with one or more books in the cart 2. Enter "Stefan" in the First Name field 3. Enter "타세프스키" in the Last Name field 4. Enter "Hollywood Boulevard" in the Street Address field 5. Enter "Los Angeles" in the Town/City field 6. Enter "90001" in the Zip Code field 7. Enter "+19512390523" in the Phone field 8. Enter "brainster1@gmail.com" in the Email Address field 9. Click on the Place Order button | An error message should be displayed and the order should not be placed successfully | The order is successfully placed without any error message |  | Stefan Tasevski | 01.06.2024 | Open
Bug014 | Order is successfully placed with invalid special characters in the last name field | Windows 10 | Opera GX 109 | High | Major | 1. Navigate to the checkout page with one or more books in the cart 2. Enter "Stefan" in the First Name field 3. Enter "Tasevski%" in the Last Name field 4. Enter "Hollywood Boulevard" in the Street Address field 5. Enter "Los Angeles" in the Town/City field 6. Enter "90001" in the Zip Code field 7. Enter "+19512390523" in the Phone field 8. Enter "brainster1@gmail.com" in the Email Address field 9. Click on the Place Order button | An error message should be displayed and the order should not be placed successfully | The order is successfully placed without any error message |  | Stefan Tasevski | 01.06.2024 | Open
Bug015 | Order is successfully placed with numbers in the last name field | Windows 10 | Opera GX 109 | High | Major | 1. Navigate to the checkout page with one or more books in the cart 2. Enter "Stefan" in the First Name field 3. Enter "Tasevski101" in the Last Name field 4. Enter "Hollywood Boulevard" in the Street Address field 5. Enter "Los Angeles" in the Town/City field 6. Enter "90001" in the Zip Code field 7. Enter "+19512390523" in the Phone field 8. Enter "brainster1@gmail.com" in the Email Address field 9. Click on the Place Order button | An error message should be displayed and the order should not be placed successfully | The order is successfully placed without any error message |  | Stefan Tasevski | 01.06.2024 | Open
Bug016 | Order is successfully placed with less than minimum characters in the street address field | Windows 10 | Opera GX 109 | High | Major | 1. Navigate to the checkout page with one or more books in the cart 2. Enter "Stefan" in the First Name field 3. Enter "Tasevski" in the Last Name field 4. Enter "Test" in the Street Address field 5. Enter "Los Angeles" in the Town/City field 6. Enter "90001" in the Zip Code field 7. Enter "+19512390523" in the Phone field 8. Enter "brainster1@gmail.com" in the Email Address field 9. Click on the Place Order button | An error message should be displayed and the order should not be placed successfully | The order is successfully placed without any error message |  | Stefan Tasevski | 01.06.2024 | Open
Bug017 | Order is successfully placed with more than maximum characters in the street address field | Windows 10 | Opera GX 109 | High | Major | 1. Navigate to the checkout page with one or more books in the cart 2. Enter "Stefan" in the First Name field 3. Enter "Tasevski" in the Last Name field 4. Enter "ThisAddressIsTooLongForThisField" in the Street Address field 5. Enter "Los Angeles" in the Town/City field 6. Enter "90001" in the Zip Code field 7. Enter "+19512390523" in the Phone field 8. Enter "brainster1@gmail.com" in the Email Address field 9. Click on the Place Order button | An error message should be displayed and the order should not be placed successfully | The order is successfully placed without any error message |  | Stefan Tasevski | 01.06.2024 | Open
Bug018 | Order is successfully placed with invalid special characters in the street address field | Windows 10 | Opera GX 109 | High | Major | 1. Navigate to the checkout page with one or more books in the cart 2. Enter "Stefan" in the First Name field 3. Enter "Tasevski" in the Last Name field 4. Enter "Hollywood^Boulevard" in the Street Address field 5. Enter "Los Angeles" in the Town/City field 6. Enter "90001" in the Zip Code field 7. Enter "+19512390523" in the Phone field 8. Enter "brainster1@gmail.com" in the Email Address field 9. Click on the Place Order button | An error message should be displayed and the order should not be placed successfully | The order is successfully placed without any error message |  | Stefan Tasevski | 01.06.2024 | Open
Bug019 | Order is successfully placed with characters that are not Latin or Cyrillic in the street address field | Windows 10 | Opera GX 109 | High | Major | 1. Navigate to the checkout page with one or more books in the cart 2. Enter "Stefan" in the First Name field 3. Enter "Tasevski" in the Last Name field 4. Enter "할리우드 대로" in the Street Address field 5. Enter "Los Angeles" in the Town/City field 6. Enter "90001" in the Zip Code field 7. Enter "+19512390523" in the Phone field 8. Enter "brainster1@gmail.com" in the Email Address field 9. Click on the Place Order button | An error message should be displayed and the order should not be placed successfully | The order is successfully placed without any error message |  | Stefan Tasevski | 01.06.2024 | Open
Bug020 | Order is successfully placed with less than minimum characters in the town/city field | Windows 10 | Opera GX 109 | High | Major | 1. Navigate to the checkout page with one or more books in the cart 2. Enter "Stefan" in the First Name field 3. Enter "Tasevski" in the Last Name field 4. Enter "Hollywood Boulevard" in the Street Address field 5. Enter "LA" in the Town/City field 6. Enter "90001" in the Zip Code field 7. Enter "+19512390523" in the Phone field 8. Enter "brainster1@gmail.com" in the Email Address field 9. Click on the Place Order button | An error message should be displayed and the order should not be placed successfully | The order is successfully placed without any error message |  | Stefan Tasevski | 01.06.2024 | Open
Bug021 | Order is successfully placed with more than maximum characters in the town/city field | Windows 10 | Opera GX 109 | High | Major | 1. Navigate to the checkout page with one or more books in the cart 2. Enter "Stefan" in the First Name field 3. Enter "Tasevski" in the Last Name field 4. Enter "Hollywood Boulevard" in the Street Address field 5. Enter "ThisCityIsWayTooLongForThisField" in the Town/City field 6. Enter "90001" in the Zip Code field 7. Enter "+19512390523" in the Phone field 8. Enter "brainster1@gmail.com" in the Email Address field 9. Click on the Place Order button | An error message should be displayed and the order should not be placed successfully | The order is successfully placed without any error message |  | Stefan Tasevski | 01.06.2024 | Open
Bug022 | Order is successfully placed with invalid special characters in the town/city field | Windows 10 | Opera GX 109 | High | Major | 1. Navigate to the checkout page with one or more books in the cart 2. Enter "Stefan" in the First Name field 3. Enter "Tasevski" in the Last Name field 4. Enter "Hollywood Boulevard" in the Street Address field 5. Enter "Los#Angeles" in the Town/City field 6. Enter "90001" in the Zip Code field 7. Enter "+19512390523" in the Phone field 8. Enter "brainster1@gmail.com" in the Email Address field 9. Click on the Place Order button | An error message should be displayed and the order should not be placed successfully | The order is successfully placed without any error message |  | Stefan Tasevski | 01.06.2024 | Open
Bug023 | Order is successfully placed with numbers in the town/city field | Windows 10 | Opera GX 109 | High | Major | 1. Navigate to the checkout page with one or more books in the cart 2. Enter "Stefan" in the First Name field 3. Enter "Tasevski" in the Last Name field 4. Enter "Hollywood Boulevard" in the Street Address field 5. Enter "Los Angeles 111" in the Town/City field 6. Enter "90001" in the Zip Code field 7. Enter "+19512390523" in the Phone field 8. Enter "brainster1@gmail.com" in the Email Address field 9. Click on the Place Order button | An error message should be displayed and the order should not be placed successfully | The order is successfully placed without any error message |  | Stefan Tasevski | 01.06.2024 | Open
Bug024 | Order is successfully placed with characters that are not Latin or Cyrillic in the town/city field | Windows 10 | Opera GX 109 | High | Major | 1. Navigate to the checkout page with one or more books in the cart 2. Enter "Stefan" in the First Name field 3. Enter "Tasevski" in the Last Name field 4. Enter "Hollywood Boulevard" in the Street Address field 5. Enter "로스 앤젤레스" in the Town/City field 6. Enter "90001" in the Zip Code field 7. Enter "+19512390523" in the Phone field 8. Enter "brainster1@gmail.com" in the Email Address field 9. Click on the Place Order button | An error message should be displayed and the order should not be placed successfully | The order is successfully placed without any error message |  | Stefan Tasevski | 01.06.2024 | Open
Bug025 | It doesn’t accept special character "+" in the Zip Code field | Windows 10 | Opera GX 109 | High | Major | 1. Navigate to the checkout page with one or more books in the cart 2. Enter "Stefan" in the First Name field 3. Enter "Tasevski" in the Last Name field 4. Enter "Hollywood Boulevard" in the Street Address field 5. Enter "Los Angeles" in the Town/City field 6. Enter "90001+" in the Zip Code field 7. Enter "+19512390523" in the Phone field 8. Enter "brainster1@gmail.com" in the Email Address field 9. Click on the Place Order button | Order should be placed successfully without any error message | Error message is displayed that the Zip Code field is required and the order is not placed successfully |  | Stefan Tasevski | 01.06.2024 | Open
Bug026 | It doesn’t accept special character "/" in the Zip Code field | Windows 10 | Opera GX 109 | High | Major | 1. Navigate to the checkout page with one or more books in the cart 2. Enter "Stefan" in the First Name field 3. Enter "Tasevski" in the Last Name field 4. Enter "Hollywood Boulevard" in the Street Address field 5. Enter "Los Angeles" in the Town/City field 6. Enter "90001/" in the Zip Code field 7. Enter "+19512390523" in the Phone field 8. Enter "brainster1@gmail.com" in the Email Address field 9. Click on the Place Order button | Order should be placed successfully without any error message | Error message is displayed that the Zip Code field is required and the order is not placed successfully |  | Stefan Tasevski | 01.06.2024 | Open
Bug027 | It doesn’t accept special character "`" in the Zip Code field | Windows 10 | Opera GX 109 | High | Major | 1. Navigate to the checkout page with one or more books in the cart 2. Enter "Stefan" in the First Name field 3. Enter "Tasevski" in the Last Name field 4. Enter "Hollywood Boulevard" in the Street Address field 5. Enter "Los Angeles" in the Town/City field 6. Enter "90001`" in the Zip Code field 7. Enter "+19512390523" in the Phone field 8. Enter "brainster1@gmail.com" in the Email Address field 9. Click on the Place Order button | Order should be placed successfully without any error message | Error message is displayed that the Zip Code field is required and the order is not placed successfully |  | Stefan Tasevski | 01.06.2024 | Open
Bug028 | It doesn’t accept special character "." in the Zip Code field | Windows 10 | Opera GX 109 | High | Major | 1. Navigate to the checkout page with one or more books in the cart 2. Enter "Stefan" in the First Name field 3. Enter "Tasevski" in the Last Name field 4. Enter "Hollywood Boulevard" in the Street Address field 5. Enter "Los Angeles" in the Town/City field 6. Enter "90001." in the Zip Code field 7. Enter "+19512390523" in the Phone field 8. Enter "brainster1@gmail.com" in the Email Address field 9. Click on the Place Order button | Order should be placed successfully without any error message | Error message is displayed that the Zip Code field is required and the order is not placed successfully |  | Stefan Tasevski | 01.06.2024 | Open
Bug029 | It doesn’t accept latin characters in the Zip Code field | Windows 10 | Opera GX 109 | High | Major | 1. Navigate to the checkout page with one or more books in the cart 2. Enter "Stefan" in the First Name field 3. Enter "Tasevski" in the Last Name field 4. Enter "Hollywood Boulevard" in the Street Address field 5. Enter "Los Angeles" in the Town/City field 6. Enter "ZipCode" in the Zip Code field 7. Enter "+19512390523" in the Phone field 8. Enter "brainster1@gmail.com" in the Email Address field 9. Click on the Place Order button | Order should be placed successfully without any error message | Error message is displayed that the Zip Code field is required and the order is not placed successfully |  | Stefan Tasevski | 01.06.2024 | Open
Bug030 | It doesn’t accept cyrillic characters in the Zip Code field | Windows 10 | Opera GX 109 | High | Major | 1. Navigate to the checkout page with one or more books in the cart 2. Enter "Stefan" in the First Name field 3. Enter "Tasevski" in the Last Name field 4. Enter "Hollywood Boulevard" in the Street Address field 5. Enter "Los Angeles" in the Town/City field 6. Enter "ЗипКод" in the Zip Code field 7. Enter "+19512390523" in the Phone field 8. Enter "brainster1@gmail.com" in the Email Address field 9. Click on the Place Order button | Order should be placed successfully without any error message | Error message is displayed that the Zip Code field is required and the order is not placed successfully |  | Stefan Tasevski | 01.06.2024 | Open
Bug031 | Order is successfully placed with less than minimum characters in the phone field | Windows 10 | Opera GX 109 | High | Major | 1. Navigate to the checkout page with one or more books in the cart 2. Enter "Stefan" in the First Name field 3. Enter "Tasevski" in the Last Name field 4. Enter "Hollywood Boulevard" in the Street Address field 5. Enter "Los Angeles" in the Town/City field 6. Enter "90001" in the Zip Code field 7. Enter "123" in the Phone field 8. Enter "brainster1@gmail.com" in the Email Address field 9. Click on the Place Order button | Order should be placed successfully without any error message | Error message is displayed that the Zip Code field is required and the order is not placed successfully |  | Stefan Tasevski | 01.06.2024 | Open
Bug032 | Order is successfully placed with more than maximum characters in the phone field | Windows 10 | Opera GX 109 | High | Major | 1. Navigate to the checkout page with one or more books in the cart 2. Enter "Stefan" in the First Name field 3. Enter "Tasevski" in the Last Name field 4. Enter "Hollywood Boulevard" in the Street Address field 5. Enter "Los Angeles" in the Town/City field 6. Enter "90001" in the Zip Code field 7. Enter "1234567890123456" in the Phone field 8. Enter "brainster1@gmail.com" in the Email Address field 9. Click on the Place Order button | Order should be placed successfully without any error message | Error message is displayed that the Zip Code field is required and the order is not placed successfully |  | Stefan Tasevski | 01.06.2024 | Open
Bug033 | User successfully submited form with name that is too short | Windows 10 | Opera GX 109 | High | Major | 1. Navigate to Contact Us page 2. Enter "S" in the Name field 3. Enter "brainster1@gmail.com" in the Email field 4. Enter "Books" in the Subject field 5. Enter "I can't buy some books" in the Details field 6. Click on Subbmit button | The form is not subbmited and that the name field is required | The form is subbmited |  | Stefan Tasevski | 07.06.2024 | Open
Bug034 | User successfully submited form with name that is too long | Windows 10 | Opera GX 109 | High | Major | 1. Navigate to Contact Us page 2. Enter "ThisNameIsWayTooLongToBeAccepted" in the Name field 3. Enter "brainster1@gmail.com" in the Email field 4. Enter "Books" in the Subject field 5. Enter "I can't buy some books" in the Details field 6. Click on Subbmit button | The form is not subbmited and that the name field is required | The form is subbmited |  | Stefan Tasevski | 07.06.2024 | Open
Bug035 | User successfully submited form with invalid special character in name field | Windows 10 | Opera GX 109 | High | Major | 1. Navigate to Contact Us page 2. Enter "Stefan#" in the Name field 3. Enter "brainster1@gmail.com" in the Email field 4. Enter "Books" in the Subject field 5. Enter "I can't buy some books" in the Details field 6. Click on Subbmit button | The form is not subbmited and that the name field is required | The form is subbmited |  | Stefan Tasevski | 07.06.2024 | Open

## Improvements
Improvement ID | Summary | Browsers Platforms & Version | Steps | Expected result | Actual result (optional)